RFQ DRR25046

March 2, 2026

Agency: California Department of Resources, Recycling and Recovery

Project Title:  Small and Medium-Sized Composting Facilities Environmental Impact Report (SB 1046), DRR25046”

CalRecycle is seeking a Contractor to complete the tasks identified within CEQA Phases 1-3, refine the Work Plan (as needed), and provide a CEQA Compliance Report to close out the project.

CEQA PHASE 1

- Develop a risk assessment that identifies and addresses issues associated with specific waste streams and the potential impacts to public health and safety and the environment, and the methods used in the models to determine potential health risks and/or hazards as a result of the development and operation of small and medium composting facilities and operations.

- Identify and recommend Best Management Practices (BMP) associated with small and medium composting facilities and operations.

- Develop and file Notice of Preparation (NOP)

REFINE WORK PLAN

- If needed, revisions to the Work Plan shall be submitted to the CalRecycle Contract Manager indicating the steps that will be taken to complete project milestones, personnel involved, and projected timeframe.

CEQA PHASE 2

- Develop, post in newspapers, and file a Notice of Availability (NOA)

- Develop and file Notice of Completion (NOC)

- Develop and file Draft EIR

- Participate in the public meeting if necessary to solicit comments during the Draft EIR public review and comment period

- Provide transcription services during the DEIR public meeting

CEQA PHASE 3

- Develop and file Final EIR

- Present Final EIR to CalRecycle for certification

- Develop and file a Notice of Determination (NOD)

PROJECT CLOSE OUT

- Prepare and submit a draft CEQA Compliance Report

- Finalize and resubmit CEQA Compliance Report

Solicitation #DRR25046

Location:	California

Due Date:	April 13, 2026 at 2:00 PM PST

Where to get notice:		www.calrecycle.ca.gov/Contracts/

Contact Information:	Contracts@calrecycle.ca.gov